## Sheet1
Id | Frage | all_of_these | 1fach_Antwort | 3-Fach_Antwort | 2-Fach_Antwort
1 | An abnormal termination of a Sprint is called when? |  | When the Product Owner determines that it makes no sense to finish it.
2 | Development Team members volunteer to own a Sprint Backlog item: |  | Never. All Sprint Backlog Items are "owned" by the entire Development Team, even though each one may be done by an individual development team member.
3 | Who is responsible for registering the work estimates during a Sprint? |  | The Development Team.
4 | When multiple teams are working together, each team should maintain a separate Product Backlog.
5 | An organization has decided to adopt Scrum, but management wants to change the terminology to fit with terminology already used. What will likely happen if this is done? | All answers apply. - Without a new vocabulary as a reminder of the change, very little change may actually happen. - The organization may not understand what has changed within Scrum and the benefits of Scrum may be lost. - Management may feel less anxious.
6 | When is a Sprint over? |  | When the timebox expires.
7 | The three pillars of empirical process control are: |  | Inspection, Transparency, Adaptation
8 | What does it mean to say that an event has a timebox? |  | The event can take no more than a maximum amount of time.
9 | When many Development Teams are working on a single product, what best describes the definition of "done"? |  | All Development Teams must have a definition of "done" that makes their combined work potentially releasable.
10 | It is mandatory that the product increment be released to production at the end of each Sprint.
11 | What is the recommended size for a Development Team (within the Scrum Team)? |  | 3 to 9
12 | Which statement best describes Scrum? |  | A framework within which complex products in complex environments are developed.
13 | Who is required to attend the Daily Scrum? |  | The Development Team.
14 | The maximum length of the Sprint Review (its timebox) is: |  | 4 hours for a monthly Sprint. For shorter Sprints it is usually shorter.
15 | What is the role of Management in Scrum? |  | Management supports the Product Owner with insights and information into high value product and system capabilities. Management supports the Scrum Master to cause organizational change that fosters empiricism, self-organization, bottom-up intelligence, and intelligent release of software.
16 | A Scrum Master is keeping a list of open impediments, but it is growing and he/she has been able to resolve only a small portion of the impediments. Which three techniques would be most helpful in this situation? |  |  | - Prioritize the list and work on them in order. - Alert management to the impediments and their impact. - Consult with the Development Team.
17 | Scrum Master is a "management" position?
18 | The Product Backlog is ordered by: |  | Whatever is deemed most appropriate by the Product Owner.
19 | Which statement best describes a Product Owner's responsibility? |  | Optimizing the value of the work the Development Team does.
20 | What is the main reason for the Scrum Master to be at the Daily Scrum? |  | He or she does not have to be there; he or she only has to ensure the Development Team has a Daily Scrum.
21 | How much work must a Development Team do to a Product Backlog item it selects for a Sprint? |  | As much as it has told the Product Owner will be done for every Product Backlog item it selects in conformance with the definition of done.
22 | Which statement best describes the Sprint Review? |  | It is when the Scrum Team and stakeholders inspect the outcome of the Sprint and figure out what to do in the upcoming Sprint. OR It gives stakeholders an opportunity to inspect the product increment and progress to date, and to provide feedback.
23 | Development Team membership should change: |  | As needed, while taking into account a short term reduction in productivity.
24 | Scrum does not have a role called "project manager."
25 | Who should know the most about the progress toward a business objective or a release, and be able to explain the alternatives most clearly? |  | The Product Owner.
26 | The CEO asks the Development Team to add a "very important" item to the current Sprint. What should the Development Team do? |  | Inform the Product Owner so he/she can work with the CEO.
27 | Who is on the Scrum Team? |  |  | - The Scrum Master - The Product Owner - The Development Team
28 | The Development Team should not be interrupted during the Sprint. The Sprint Goal should remain intact. These are conditions that foster creativity, quality and productivity. Based on this, which of the following is false? |  | The Sprint Backlog and its contents are fully formulated in the Sprint Planning meeting and do not change during the Sprint.
29 | The timebox for a Daily Scrum is? |  | 15 minutes.
30 | Which two (2) things does the Development Team not do during the first Sprint? Which two doesn't the Team do during the first Sprint? |  |  |  | - Nail down the complete architecture and infrastructure. - Develop a plan for the rest of the project.
31 | Why is the Daily Scrum held at the same time and same place? |  | The consistency reduces complexity and overhead.
32 | The Development Team should have all the skills needed to: The Team should have all the skills needed to: |  | Turn the Product Backlog items it selects into an increment of potentially shippable product functionality.
33 | Upon what type of process control is Scrum based? |  | Empirical
34 | What is the primary way a Scrum Master keeps a Development Team working at its highest level of productivity? |  | By facilitating Development Team decisions and removing impediments.
35 | The timebox for the complete Sprint Planning meeting is? |  | 8 hours for a monthly Sprint. For shorter Sprints it is usually shorter.
36 | Who has the last say on the order of the Product Backlog? |  | The Product Owner
37 | What is the maximum length of a Sprint? | All of these answers are correct. - Not so long that the risk is unacceptable to the Product Owner. - Not so long that other business events can't be readily synchronized with the development work. - No more than one calendar month.
38 | The Scrum Master should not allow the Product Owner to got to the Sprint Planning Meeting without having already devised the Sprint Goal
39 | Which output from Sprint Planning Meeting provides the Development Team with a target overarching direction for the Sprint? |  | The Sprint Goal
40 | When is the Sprint Backlog created? |  | During the Sprint Planning meeting.
41 | Which of these may a Development Team deliver at the end of a Sprint (choose 2)? |  |  |  | - A single document, if that is what the Product Owner asked for. - An increment of working software that is "done"
42 | What things might a Scrum Product Owner focus on the ensure his product delivers value? |  |  | - How readily his product can be absorbed and used by his customers. - How much of the functionality of his product is being utilized. - Direct customer feedback.
43 | Which of the following are required by Scrum? | Non of the above - Release burndown diagram - Burndown chart - Feature burn-up - Crtical Path Analysis - Refactoring - Project gantt chart
44 | Which of the following are true about the Product Owner role? (Select all that apply) |  |  | - The PO can be influenced by a Committee - The PO is accountable for ordering the Product Backlog - The PO is one person
45 | Scrum is a methodology that tells in detail how to build software incrementally
46 | Items on the Product Backlog tend to be: |  | - Larger than the items in the Sprint Backlog.
47 | What are advantages of a Product Owner with a solid product vision? |  |  | - It is easier to inspect incremental progress at the Sprint Review. - It helps the Scrum Team keep focus and they can check any decision against it, event within a Sprint. - It gives a good overall direction so Sprints will feel less as isolated pieces of work.
48 | The Sprint Goal is a result from Sprint Planning, as is Sprint Backlog.
49 | To be able to validate work by the Development Team as done, it is the Product Owner's to write acceptance tests for all User Stories.
50 | Which of the following practices might help the Product Owner minimize waste in developing and sustaining the Product Backlog? (Choose all answers that apply). |  |  | - Write or cause Product Backlog items to be written clearly, and with as little ambiguity as possible - Only fully describe Product Backlog items when it seems sure that they are likely to be turned into product or system functionality
51 | Why might the Product Owner care that a team builds high quality software and adheres to it's definition of done? (Choose 2 answers) |  |  |  | - To control the Total Cost of Ownership of the product. - To have complete transparency into what has been done at the end of each Sprint.
52 | Every Scrum Team must have a Product Owner and Scrum Master. |  | Yes, and each Scrum Team's performance may be affected by their degree of participation as influenced by any other responsibilities (e. g. other teams for which they are also the SM or PO)
53 |  |  | There are no such activities. The next Sprint starts immediately after the current Sprint.
54 | For which is the Scrum Master responsible? |  | - The Scrum process being adopted and used properly.
55 | The Product Owner makes sure the right stakeholders are invited to the Sprint Retrospective. They might have important instructions for team improvements.
56 | During a Sprint Retrospective, for what is the Product Owner responsible? |  | - Participating as a Scrum Team member.
57 | All work to be done by the Development Team must ultimately originate from the Product Backlog?
58 | When many Scrum teams are working on the same product, should all of their increments be integrated every Sprint? |  | Yes, otherwise the Product Owners (and stakeholders) may not be able to accurately inspect what is done.
59 | A "cone of uncertainty" can be used to do what? |  | Help a Product Owner estimate how much work is likely to be done during a certain number of Sprints.
60 | Who should make sure everyone does his or her tasks for the Sprint? |  | The development team
61 | Which of the following two items are not topics of discussion within a Sprint Retrospective? |  |  |  | - Sprint Backlog for the next Sprint - Functionality implemented as a result of the Sprint
62 | What are some consequences if a Development Team does not have a consistent of done from Sprint to Sprint? | All of the above. - The DEV may not know how many Product Backlog items it can Sprint. - The PO may not know what he/she is inspecting at the Sprint Review - The PO may be unable to gauge the progress toward his/her go - The DEV may not know what work is entailed in completing the Product Backlog items.
63 | Which three activities will a Product Owner likely engage in during a Sprint? |  |  | - Answer questions from the DEV Team about items in the current Sprint. - Work with the stakeholders - Provide feedback.
64 | Who is responsible for engaging the stakeholders? |  | - The Product Owner
65 | Why should the Product Owner be present at the Daily Scrum? |  | - He/she doesn't need to be there.
66 | How many hours per day should a person on a Scrum team work? |  | - A sustainable pace, usually from 7-8 hours per day.
67 | A Product Backlog is: (choose 3 answers) |  |  | - An inventory of things to be done. - Managed by the Product Owner. - Ordered based on priority, value, dependencies, and risk.
68 | If quality assurance work does not occur as part of the development work within a Sprint, which benefits are lost? |  |  | - The increment probably is not potentially shippable. - The Product Backlog burndown is not transparent - the next sprint will probably interrupted with bugs that are beeing found
69 | How much time is required after a Sprint to prepare for the next Sprint? |  | None. A new Sprint starts immediately following the end of the previous Sprint.
70 | Who is responsible for tracking the remaining work of the Sprint? |  | The Development Team
71 | If burndown charts are used to visualize progress, what does it track? |  | Work remaining across time.
72 | When should the Product Owner update the project plan? |  | Product Backlog is the plan in Scrum. It is updated as new information and insights emerge.
73 | When a Development Team determines that it has over-committed itself for a Sprint, who has to be present when reviewing and adjusting the Sprint work selected? |  | The Product Owner and Development Team
74 | Drawing a trend line through a release burndown chart indicates? |  | When the work remaining will likely be completed if nothing changes on the backlog or the Development Team.
75 | Which of the following are true about the length of the Sprint? (Slect all that apply.) |  |  |  | - All Sprints must be 1 month or less - It is best to have Sprints of consistent length throughout a development effort.
76 | Which three questions are answered by all Development Team members at the Daily Scrum? |  |  | - What work did I do yesterday? - What impediments are in my way? - What work am I going to do today?
77 | Which of the following are feedback loops in Scrum? |  |  | - Daily Scrum - Sprint Review - Sprint retrospecitve
78 | As the Sprint Planning meeting progresses, the workload is getting to be greater than the Development Team's capacity. Which two actions make the most sense to do? |  |  |  | - Potentially remove or change selected Product Backlog items. - The Development Team should ensure that the Product Owner is aware. Then, start to Sprint and monitor burndown rates.
79 | The Product Owner creates all of the Product Backlog items (e.g. user stories, non-functional requirements, etc.) on the Product Backlog?
80 | Which phrase best describes a Product Owner? |  | Value optimizer
81 | A Sprint Review is the only time that te stakeholders and the Scrum Team come together.
82 | The primary job of a Product Owner is to: |  | - Maximize the value of the work that the Development Team delivers.
83 | Which of the following are true about the Scrum Master role? (Select all that apply.) |  |  |  | - The SM teaches the Development Team to keep the Scrum meetings to their timebox - The SM helps those outside the team interact with the Scrum Team.
84 | Which statement best describes the Sprint Backlog as outcome of the Sprint Planning? |  | It is a decomposition of Product Backlog items such that enough work is decomposed for at least the first days of the Sprint.
85 | The Product Owner makes sure the team selects enough from the Product Backlog for a Sprint to satisfy the stakeholders.
86 | Which of the following is required by Scrum? |  | - Sprint Retrospective
87 | Who determines when it is appropriate to update the Sprint Backlog during a Sprint? |  | The Development Team
88 | The Product Owner should have a complete and exhaustive Product Backlog before the first Sprint can start?
89 | What is the role of the Product Owner in crafting the Sprint Goal? |  | The Product Owner should come to the Sprint Planning with a business objective in mind and work with the Development Team to craft the Sprint Goal based upon the forecast.
90 | My job as a Product Owner focuses on the following: (choose 2 answers.) |  |  |  | - Working with customers and stakeholders to identifiy the most important product requirements. - Clearly communicating project or release status and strategies to customers and stakeholders
91 | Who is responsible for clearly expressing Product Backlog items? |  | The Product Owner
92 | Who must conform to the definition of done? |  | The Scrum Team
93 | What typically happens if Product Backlog is not sufficiently clear at Sprint Planning? |  | The Development Team has difficulties creating a forecast of work for the Sprint
94 | A PO (Product Owner) is essentially the same thing as a traditional PM (Project Manager).
95 | The Product Owner determines how many Product Backlog items the Development Team selects for a Sprint.
96 | What happens if the Development Team cannot complete its work by the end of a timebox? |  | Timebox holds and development team gradually learns to only do what is possible within the timebox.
97 | While under development, the environment in which a product will be used changes and emerges. What is the effet on the Product Backlog? |  | It evolves to reflect what the product needs to be most valuable.
98 | Which of the following is the Development Team NOT responsible for? |  | Selecting the Product Owner
99 | Software dependencies could influence how the Product Owner orders Product Backlog items.
100 | When should the Product Backlog for a Sprint be refined (Select all that apply.) |  |  |  | - The PO and the DEV do it in the actual Sprint if they haven't been able to do it in preceding Sprints. - The PO an dthe DEV do it in the 1-2 preceding Sprints.
101 | The Development Team finds out during the Sprint that they aren't likely to build everything they forecasted. What would you expect a Product Owner to do? |  | Re-work the selected Product Backlog items with the Development Team to meet the Sprint Goal.
102 |  |  |  |  | - Work with the Development Team on Product Backlog refinement. - Collaborate with stakeholders, user communities and product managers.
103 | Which of the following is an example of an increment of working software? |  | Additional features that complement those delivered in previous iterations
104 | When does the second Sprint start? |  | Immediately after the first Sprint.
105 | The Definition of Done is used to: (Select three answers.) |  |  | - Increase transparency. - Guide the Development Team on how many Product Backlog items to select in a Sprint. - Create a shared understanding of when work is complete.
106 | Which technique is the LEAST productive way for the Scrum Master to ensure that the Development Team communicates effectively with the Product Owner? |  | Act as a go-between for them.
107 | How much of the Sprint Backlog must be defined during the Sprint Planning meeting? |  | Enough so the Development Team can create its best forecast of what it can do, and to start the first several days of the Sprint.
108 | The only person who can abnormally terminate a Sprint is? |  | The Product Owner
109 | What might indicate to a Product Owner that she needs to work more with the Scrum Team? |  | The increment presented at the Sprint Review does not reflect what she thought she had asked for.
110 | Why is it important that there is only one Product Owner per product? (choose 3 answers.) |  |  | - It helps avoid barriers to effective communication and rapid decision-making. - The DEV always knows who determines priorities. - It is clear who is accountabile for the ultimate success of the product.
111 | As the Product Owner is accountable for the end result, he/she has the final say over the Definition of Done?
112 | Which of the following might the Scrum Team discuss during a Sprint Retrospective? | All of the above. - Methods of communication. - The way the Scrum Team does Sprint Planning. - Skills needed to improve the Development Team's ability to deliver. - Its Definition of Done.
113 | Which topics should be discussed in the Sprint Review? |  | Sprint results
114 | Who creates a Product Backlog item's estimate? |  | The Development Team after clarifying requirements with the Product Owner OR The Scrum Master. AND The Product Owner with input from the Team.
115 | Which of the following is true about Scrum? (Select all that apply.) |  |  | - Scrum is a framework for developing and maintaining complex products. - Each component of Scrum serves a specific purpose and is essential fo Scrum's success and your usage of Scrum to develop complex products. - Scrum is based on empirical process control theory
116 | To get started, Scrum requires no more than a Product Owner with enough solid ideas for a first Sprint, and a Development Team to implement those ideas.
117 | What is included in the Sprint Backlog? | Any of the above (or others) which is a decomposition of the selected Product Backlog items. - User Stories - Tasks - Use Cases - Tests
118 | The Product Owner must ship each Sprint increment. |  | When it makes sense.
119 | As Scrum Teams mature, it is expected that: |  | They will improve their Definition of Done to include more stringent criteria
120 | A Sprint Retrospective should be held: |  | At the end of each Sprint.
121 | why does a Development team need a Sprint Goal |  | The goal focuses the development team on a common yet specific goal.
122 | The timebox for the Sprint Review is? |  | 4 hours for a 4 week sprint. Usually shorter for shorter Sprints.
123 | What are the benefits of self-organization to the Scrum Development Team? |  |  | - Increased creativity - increased commitment - increased feeling of accountability
129 | When is a Product Backlog item considered complete? |  | The item has no work remaining that must still be done before it can be used by its end user. OR When it conforms to the definition of done for that Team.
125 | Which answer best describes the topics covered in Sprint Planning? |  | What can be done and how to do it
126 | The Development Team has forecast an amount of Product Backlog Items it thinks it can accomplish and a Sprint goal. Who determines how the development team accomplishes this work? |  | The Development Team
127 | What are the responsibiliteis of a tester in an Development Team (choose 2)? |  |  |  | - There is no spedific tester role - Everyone is responsible for quality in Scrum
128 | Sprint burndown charts are an efficient tracking tool because they show: |  | Estimated work remainting for the Sprint.
124 | When determining the ordering of an item on a Product Backlog, what are some things a Product Owner shoupd consider? |  |  | - Risk - Alignment with business strategy an goals - Importance to customer - Alignment and dependencies with exiting Procut Backlog Items
130 | Which of the below are roles of a Scrum Team? |  |  | - Product Owner - Scrum Master - Development Team
131 | Which two are properties of the Daily Scrum? (Choose 2) |  |  |  | - It is fifteen minutes or less in duration. - Ist location and time should remain constant.
132 | What is the accountability of the Product Owner during Sprint 0? |  | There is no such thing as Sprint 0.
133 | Which best describes the Product Backlog? |  | It is allowed to grow and change as more is learned about the product and ist customers.
134 | Which of the following best describes an increment of working software? |  | Additional features in a useable state that complement those delivered in previous iterations.
135 | What is NOT a benefit of self-organization to the Scrum Development Team? |  | Management can remove a failling resource more easely
136 | When does the next Sprint begin? |  | Immediately after the conclusion of the previous Sprint.
137 | The purpose of a Sprint is to have a working increment of product done before the Sprint Review.
138 | During the Daily Scrum, the Scrum Master … |  | Facilitate discussions of the Development Team
139 | The primary reason one might choose a four-week Sprint is when the work is too large for a two -week Sprint and cannot be decomposed further
140 | During a Sprint, when is new work or further decomposition of work added to the Sprint Backlog? |  | As soon as possible after they are identified.
141 | Which two things does a Scrum Master do if the Development Team doesn't have the engineering tools and infrastructure to completly finish any Product Backlog items? (choose 2) |  |  |  | - Asks the Development Team to spend as many Sprints as necessary to prepare the engineering tools and infrastructure so any Product Backlog item it selects is potentially shippable at Sprint end. - Has the Development Team improve ist skills / tools and infrastructure over time and adjust the definition of "done" accordingly.
142 | A properly functioning Scrum team will have at least one Release Sprint and may well have several.
143 | What does it mean for a Development Team to be cross-functional? |  | The Development Team includes cross-skilled individuals who are able to contribute to do what is necessary to deliver an increment of software
144 | During the Sprint, the Scrum Master's role is to |  |  |  | - Remove impediments - Facilitate inspection and adaption opportunities….
145 | A Scrum Master is working with a Development Team that has memebers in different physical locations. The Development Team meets in a variety of meeting rooms and has much to do logistically (for example, set up conference calls) before beginning the Daily Scrum. What action should the Scrum Master take? |  | Allow the Dev. Team to self-manage and determine for itself what to do.
146 | A new developer has joined an existing Scrum team. He/she is having continuing conflicts with existing members and is making the environment hostile. If necessary, who is responsible for removing the new team meber, and why? |  | d
147 | How is management external to the scrum Team involved in the Daily Scrum? |  | The Product Owner represents their opinions.
148 | When does a Development Team make adjustments to ist engineering practices? |  | After they have been discussed and agreed to at the Sprint Retrospective.
149 | For the purpose of transparency, when does Scrum say a new increment of working software must be available? |  | At the end of every Sprint.
150 | Who must do all the work to make sure that Product Backlog items conform to the Definition of Done? |  | The Development Team
151 | Which are functions of a self-organizing Development Team in Scrum ? Choose all that apply. |  |  | - Undertake the work in the Sprint Backlog - Pull work from the Product Backlog into the Sprint - Set the best time for the Daily Scrum
152 | The Team has committed to Product Backlog and a Sprint goal. Who determines how it accomplishes this work? |  | The Team
153 | A Scrum Master is introducing Scrum to a new Team. The Team has decided that a retrospective is unnecessary. What action should the Scrum Master take? |  | Describe the function, purpose and importance of the retrospective.
154 | The CEO asks the Team to add a story to the current Sprint. What should the Team do? |  | Inform the Product Owner so he/she can work with the CEO.
155 | Why is it important for a Team to have a consistent definition of done from Sprint to Sprint? |  | All of the above: So the Team knows how many Product Backlog items it can do in a Sprint. So the Product Owner knows what he/she is inspecting at the Sprint Review. So the Product Owner can gauge the progress toward his/her goals. So the Team knows what work is entailed in completing selected Product Backlog items.
156 | Since no new work can be added to a Sprint, what is the appropriate characteristic of the Sprint Backlog during the Sprint? |  | The Sprint Backlog emerges to reflect the work needed to develop Product Backlog items.
157 | The Product Backlog is sorted by |  | Least valuable items at the bottom to most valuable at the top.
158 | During a Sprint Retrospective, for what is the Scrum Master responsible? |  | Facilitating and also participating as a Scrum team member
159 | When a Team determines that it has overcommitted itself for a Sprint, who has to be present when reviewing and adjusting the Sprint goal and work? |  | The Scrum Master, project manager and Team.
160 | The reason the Scrum Master is at the Daily Scrum is: |  | They only have to ensure the Team has a Daily Scrum.
161 | The top priority items of the Product Backlog should be analyzed. estimated, and prioritized adequately to begin a sprint. This is referred to as an 'actionable' Product Backlog. Which approach would you recommend to ensure that this is true, Sprint by Sprint, in a twelve Sprint project. |  | Set aside time each Sprint for the Scrum Team to analyze, estimate and prioritize the Product Backlog so it always stays actionable. This work usually occupies 10% of a Sprint and the mechanism for doing this work is up to the Scrum Team to devise and revise.
162 | What two main topics does the Sprint Planning meeting cover ? |  | What to do how to do it
163 | In order to maximize the value of the product, a Product Owner needs awareness of the following: |  | None of the above - competive research - customer feedback - vision - forecasting… - all of the above
164 | What is typical work for a Product Owner in a Spring? Choose 2 answers |  |  |  | - work with the Developement Team on Product Backlog refinement - Collaborate with stakeholders, user communities and product managers
165 | The key customer to be satisfied is |  | User of my product
166 | When should the Proudct Backlog for a Sprint be refined? Choose 2 answers |  |  |  | The Product Owner and the Development Team do it in the 1-2 preceding Sprints - The Product Owner and the Development Team do it in the actual Sprint if they haven't been able to do it in preceding Sprints
167 | What are criteria to order Product Backlog items | all of the above: - Value - Depencies between items - Depencies products
168 | What is typical Product Owner work that a Product Owner might delegate |  | Write User Stories
169 | The Product Owner remains distant. He/she has handed over the required Product Backlod for the Sprint but is not collaboratin with the Development Team durch the Sprint. What are valuable action for a Scrum master? Choose all that apply |  |  | - Coach the Product Owner in the values of Scrum and - incremental delivery. - Bring up the problem in the Sprint Retrospective
170 | A done Increment is valuable if: Choose 2 answers |  |  |  | - It is likely to increase customer satisfaction - It reduces long-term operational costs
171 | What percent of the time should a Product Owner dedicate to the Scrum Team? Choose all that apply |  |  |  | - 40%, or mor if the stakeholder agree - Enough time to ensure that the product increment has the functionality an dthe funtional coherence to make sense for stakteholder an users.
172 | The Product owner must use:
173 | Sprint Reviews are an opportunge time to collect customer feedback
174 | If work is to be done by the Development Team, is must have ultimately originated rom the Product Backlog?
175 | Which two metrics will help a Product Owner that value is being delivered? |  |  | - Time to market - Customer satisfaction
176 | What sources may a Product Owner use when considering the value of a product? Choose all that apply |  |  | - VP of Sales - Customers and Prospects - Market Research